## Defect Tracking Register
IT-TMP-027-Defect Tracking Register Template
|  |  |  | GRG - UAT DEFECT TRACKING REGISTER | [10 empty] | Version: 1.0
Effective Date: 11/08/2026
[11 empty] | For the period from: | 11/08/2026 |  | to | 11/08/2026
PART 1: PROJECT INFORMATION
Program Name | GRG CRM Banking Solution | [7 empty] | Program # |  |  | IT PM
Project Name | People's Bank CRM Testing & Integration | [7 empty] | Project # |  |  | Business PM
Project Sponsor | People's Bank IT Department | [7 empty] | Project Manager |  |  | Project Start Date
PART 2: DEFECTS
Origin (Build) | Defect No. | Defect Description | Steps to Reproduce | Expected Results | Defect Attachment | CR Reference | Application / Module | Defect Category | Severity | Priority | Defect Status | Detected By | Date of Defect Origin | Assigned To | Expected Date of Closure | Fixing Date | Closed By | Date of Closure | SLA = (Date of Closure - Expected date of Closure) | Comments | Comments | Status - 13/08/2026 | Status - 14/08/2026 | Status - 17/08/2026
CRM V1 | TC_CD_CB_N_01_009 | Test case not applicable. For the "Press Cancel on telephone entry screen" scenario, this is invalid as there is no screen for telephone number entry in the current flow. | Press Cancel on telephone entry screen | Transaction cancelled, card ejected, and thank you screen displayed. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Not applicable | This scenario does not exist in the implemented functionality and should be considered Not Applicable | N/A | N/A | N/A
CRM V1 | TC_CD_CB_N_01_010 | Invalid remarks entry (rules defined or enforced for remarks field) | Enter remarks violating validation rules | Invalid information or character limit warning message displayed. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | No validation rules defined or enforced for remarks field. | This test case cannot be validated at present, as no specific rules, conditions, or validation criteria have been provided by the relevant team for the Remarks field. Therefore, the expected behavior for an invalid Remarks entry cannot be determined or verified at this stage. Kindly provide the required validation rules and conditions for the Remarks field so that the test case can be executed accordingly | Pending | Pending | Pending
CRM V1 | TC_CB_BP_PIC_PLC_N_01_005 | For Dialog bill payments transaction allowed for 9 digits invalid telephone number | Enter invalid telephone number and confirm | Error information message displayed. |  |  | Card Based PIC PLC-Negetive | Card Based | Medium | Medium | Open | Channel Team |  | Development Team | [5 empty] | Telephone number is not validating. | We will inform the BPC team to add a validation rule to verify that the phone number begins with the prefix "07". And Informed PB API dev team | Pending | Pending | Pending
CRM V1 | TC_CB_CW_P_01_007 | E-receipt unavailable, If there's paper receipt unavailable it's not asking for E-receipt option and transaction proceed successfully without any receipt | Insert Card > Select PIN > Select Withdrawal > Accept "No Receipt / E-Receipt" prompt > Enter amount > Confirm | Cash dispensed successfully, e-receipt/SMS sent to mobile number, no paper printed, card ejected. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | E-receipt option is unavailble. | Already informed BPC team. | Pending | Pending | Pending
CRM V1 | TC_CL_BP_P_01_011 |  | Select payment > Receipt unavailable > Agree e-receipt message > Complete valid payment flow | Transaction completed successfully and e-receipt sent |  |  | Cardless Bill Payment-Positive | Cardless | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | No e receipt option available. | Already informed BPC team. | Pending | Pending | Pending
CRM V1 | TC_CB_CW_P_01_008 | Verify multiple consecutive cash withdrawals in a single session | Insert Card > Select PIN > Perform 1st Withdrawal > Take Cash > Select Another Transaction > Perform 2nd Withdrawal > Confirm | Both transactions complete successfully, individual CBS debit postings recorded, receipts issued, and card ejected at end. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | There’s no “would you like another service” screen | This test case is not applicable to the current CRM transaction flow. There is no defined or supported scenario for performing multiple consecutive cash withdrawals within a single session | Pending | N/A | N/A
CRM V1 | TC_CB_CR_P_01_003 | Credit card function is not working, if we try to do any transaction it shows as "Last Transaction Cancelled" | Insert card & enter PIN > Select 'Cash Advance’ > Input custom amount (LKR 15,000) > Confirm. | 1. LKR 15,000 cash dispensed. 2. Balance updated in SIBS. 3. Receipt generated. 4. Card returned. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Last transaction cancelled | Master credit card is working Visa credit card is not working | Master card is working, VISA card is not woking | Pending | Pending
CRM V1 | TC_CB_CD_P_01_004 | 10 Digits validated only, phone number is not verified | Enter valid telephone number and confirm | Telephone verified through SV and purpose screen displayed. |  |  | Card_Based_Cash Deposit-Positiv | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | phone number is not verified | Informed PB API dev team | Pending | Pending | Pending
CRM V1 | TC_CB_BP_PIC_PLC_P_01_004 | Need to be developed Service charge agree or disagree screen. | Enter valid telephone number and confirm | Process continues with charge confirmation. |  |  | Card Based PIC PLC-Positive | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Need to be developed Service charge agree or disagree screen. | This test case is not applicable to the current transaction flow, as there are no service charges applicable to this scenario. Therefore, a Charge Confirmation screen is not required for this transaction | Pending | Pending | Pending
CRM V1 | TC_CD_CB_N_01_008 | When we performing payments through card it doesn't have telephone number entry | Enter telephone number failing API/SV validation | Error prompt displayed on screen. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Not applicable | This test case is not applicable to the current transaction flow. When performing payments through a card, there is no Telephone Number Entry step in the implemented flow. Therefore, this scenario cannot be executed | N/A | N/A | N/A
CRM V1 | TC_CB_SLIC_GENERAL_N_01_001 | When an invalid or non-existent SLIC General Insurance customer reference number is entered it’s not giving any error message | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select SLIC > Select General Insurance > Enter Invalid Customer Reference Number > Enter Amount > Select Account > Confirm Bill Payment | System displays an error message (e.g., "Invalid Customer Reference") and prevents proceeding to confirmation. |  |  | Card_Based_SLIC_GENERAL_Negative | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Customer Ref number is not verified, Ref no - 123456789 amount - 500 acc - 204200260002632 | This scenario will be verified during Pilot Testing | Pending | Pending | Pending
CRM V1 | TC_CB_SLIC_LIFE_N_01_001 | When an invalid or non-existent SLIC Life Insurance customer reference number is entered it’s not giving any error message | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select SLIC > Select Life Insurance > Enter Invalid Customer Reference Number > Enter Amount > Select Account > Confirm Bill Payment | System displays an error message (e.g., "Invalid Customer Reference") and blocks the transaction from completing. | TC_CB_SLIC_LIFE_N_01_001_17864238333255983866130094259887.jpg |  | Card_Based_SLIC_LIFE_Negative | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Customer Ref number is not verified | This scenario will be verified during Pilot Testing | Pending | Pending | Pending
CRM V1 | TC_CB_CW_N_01_011 | If one cassette is empty, all cassette showing as blocked and can’t perform withdrawal | Insert Card > Enter PIN > Select Withdrawal > Enter valid amount | System should process successfully without errors |  |  | Card Based Cash Withdrawal-Nega | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | If one cassette is empty, all cassette showing as blocked and cant perform withdrawal | Need to inform vendor | Completed | Completed | Completed
CRM V1 | TC_CB_CR_P_01_001 | Credit card function is not working, if we try to do any transaction it shows as "Last Transaction Cancelled" | Insert Mastercard > Select Language > Enter valid PIN > Select 'Balance Inquiry’ > Press 'Proceed'. | 1. Screen displays Actual & Available balance. 2. Receipt printed with RRN & STAN/UTANO. 3. Card ejected cleanly. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-09 00:00:00 | Development Team | [5 empty] | Last transaction cancelled | Master credit card is working Visa credit card is not working | Morning Master credit card is worked, after 2PM it’s not worked Visa credit card is not working | Pending | Pending
CRM V1 | TC_CB_CR_P_01_002 |  | Insert card & enter PIN > Select 'Cash Advance’ > Select preset amount (LKR 10,000) > Confirm transaction. | 1. Cash dispensed (LKR 10,000). 2. Limit reduced in SIBS. 3. Receipt printed with RRN/UTANO. 4. Card ejected. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Last transaction cancelled | Master credit card is working Visa credit card is not working | Morning Master credit card is worked, after 2PM it’s not worked Visa credit card is not working | Pending | Pending
CRM V1 | TC_CB_CW_P_01_004 | If we request more than daily limit (Eg:>200000) machine gives following 2 screens instead of "daily limit exceed" screen 1. Unable to dispense, sorry for the inconvenience, Thank you for banking with us. 2. Unable to dispense, Enter the multiple of (amount) | Insert Card > Select PIN > Select Withdrawal > Enter max single transaction limit (e.g., Rs. 40,000 / Rs. 100,000) > Confirm | System processes max limit, dispenses notes, updates SIBS/CBS balance, and prints receipt. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | "daily limit exceed" screen is not displayed | Informed BPC team | Completed | Completed | Completed
CRM V1 | TC_CB_CW_OBC_P_01_001 | Other bank card navigation is completely wrong for the all language | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Saving Account > Enter valid amount(eg - Rs.5000.00) > Take cash | Transaction is approved, cash is dispensed, receipt is printed, and card is returned successfully. |  |  | Other Bank Card function - Positive | Card Based | High | High | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Some function are missing in all 3 language | Informed BPC team | Pending | Partially completed(In Tamil language Screen and Flow wrong) | Pending
CRM V1 | TC_CB_CW_OBC_P_01_002 | For other banks card pin entry, machine doesn’t allowed transactions for 4 digits pin entry. It’s allowed for only 6 digit pin entry. | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Current Account > Enter valid amount(eg - Rs.5000.00) > Take cash | Transaction is processed successfully, cash is dispensed, and physical/digital receipt is provided. |  |  | Other Bank Card function - Positive | Card Based | High | High | Open | Channel Team | 2026-08-11 | Development Team | [5 empty] | PIN entries not functioning properly | Informed BPC team PBKI-527 | Pending | Completed | Pending
CRM V1 | Card Reader / Initialization Flow | Verify system behavior when a card is inserted and immediately navigates to the language selection screen, but intermittently displays a "Last Transaction Cancelled" message and rejects the card. | Insert Card > Navigate immediately to the language selection screen | The system handles the card read state without false cancellation triggers; if an exception or intermittent timeout occurs, it displays the specific "Last Transaction Cancelled" warning message cleanly, ejects/rejects the card safely, and resets to the welcome screen without locking up the card reader module. |  |  | N/A | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | When we get the journal log it showed as “PIN PAD FAILED” “506 /\ 14:22:32 INSERVICE MODE 14:22:32 798 /\ 14:22:32 INSERVICE MODE 14:22:32 820 SCREEN : 021 14:22:34 285 && PINPAD FAILED, CANCEL TRANSACTION 14:25:53 615 14:25:53 615 2026/08/11 14:25:53 SYSTEM STARTUP 14:25:53 615 ********************************** 14:25:53 617 KERNEL VERSION:3.0.2.906 14:25:53 617 PROJECT VERSION:ECAT(PB_P2800NL)3.0.2.906(XDC)-B8 14:25:53 617 ATM NUMBER:72172128 14:25:53 617 BANK NUMBER:1234 14:25:53 617 BRANCH NUMBER:5678 14:25:53 617 ATM TYPE:P2800NL 14:25:53 646 LOCAL IP:10.230.98.27 14:25:53 646 HOST IP:(ATMP1):172.18.25.114:6000 | Informed vendor | Pending | Pending | Pending
CRM V1 | Cash Withdrawal Amount Entry UI | Verify system behavior when a user enters an amount (e.g., 123456.00) on the withdrawal amount entry screen and touches the first digit after the decimal point (6), checking if it unexpectedly navigates backward to the transaction type selection screen. | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Current Account > Enter valid amount 123456.00 > Touch the first digit after the decimal point (6) | The system maintains focus on the input field or correctly handles the touch input without triggering a navigation event; it should not unexpectedly jump backward to the transaction type selection screen. |  |  | N/A | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Touch coordinate mapping or event listener on the numeric keypad/decimal input field is misconfigured, causing it to double-fire or misinterpret the touch action as a "Back" or "Cancel" command. Needs UI component re-mapping. | Informed vendor | Pending | Pending | Pending
CRM V1 | TC_CB_Sup_N_01_010 | Through the Admin card without receipt if we try to get the list total it gave message as "Transaction successful, Would you like another transaction", through terminal if we try to get E-journal it gave error message as "Print unsuccessfully" | Select Print Audit Report / EJ Journal | System detects paper out status, displays "Printer Paper Empty" error, and logs report to electronic journal. |  |  | Admin _ Supervisor Functions-Ne | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Through the Admin card without receipt if we try to get the list total it gave message as "Transaction successful, Would you like another transaction", through terminal if we try to get E-journal it gave error message as "Print unsuccessfully" | Informed BPC team | Pending | Pending | Completed (But the error message is wrong it gave as “Last Transaction is cancelled)
CRM V1 | TC_CB_CR_P_01_001 | Credit card bill payment is not working | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select Credit Card bill payment > Enter Invalid Account Number > Enter Amount > Select Account > Confirm Bill Payment | Transaction is processed successfully, and physical receipt is provided and card is ejected |  |  | Card_Based_Credit_Positive | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Credit card bill payment is not working | Informed PB API dev team | Pending | Pending | Pending
CRM V1 | Cabinet / Safe Door Interlock Switch | Verify that opening the physical cabinet/safe door of the GRG machine correctly triggers the hardware interlock switch to take the machine out of "In-Service" and transition it into "Supervisor / Maintenance Mode". | Physically open the cabinet/safe door of the GRG machine > Observe the application screen and machine status | The system immediately detects the open door signal, takes the machine "Out of Service" for normal customer transactions, and automatically prompts or transitions into the Supervisor / Maintenance Mode interface. |  |  | N/A | N/A | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | The hardware limit switch, door microswitch, or signal line to the mainboard is failing to register the door opening event, or the software service handler is ignoring the interlock input. This poses a security and operational compliance risk. | This scenario cannot be practically executed as part of the normal CRM transaction flow and should be considered Not Applicable | N/A(even if came to inservice we cant proceed ant transaction) | N/A(even if came to inservice we cant proceed ant transaction) | N/A(even if came to inservice we cant proceed ant transaction)
CRM V1 | N/A | Navigate to Cardless Cash Deposit or Cash-Based Bill Payment, enter the required details, insert cash, press the Confirm button, and observe that the system prematurely flashes the success screen before incorrectly reverting backward to display the "Please wait your cash being verified" processing screen. | Navigate to Cardless Cash Deposit or Cash-Based Bill Payment, enter the required details, insert cash, press the Confirm button, and observe that the system prematurely flashes the success screen before incorrectly reverting backward to display the "Please wait your cash being verified" processing screen. | The system should display the cash verification and processing screen first, finalize the transaction securely, and only show the success screen after processing is fully complete. |  |  | CRM Cash Deposit & Bill Payment Flow | N/A | High | High | Open | Channel Team | 2026-08-13 | Development Team | [5 empty] | This state machine inversion/glitch misleads users into believing the transaction has completely finished before validation and backend posting are actually done. |  | Pending | Pending | Pending
CRM V1 | N/A | During cash deposits containing LKR 2000 notes alongside other denominations, the physical notes route correctly (LKR 2000 notes go to the All-In-One cassette while other denominations go to their respective cassettes), but the total receipt list and transaction summary incorrectly state that all deposited denominations went to the All-In-One cassette. | 1. Perform a cash deposit transaction including LKR 2000 notes alongside other denominations. 2. Complete the deposit and verify physical cassette routing. 3. Print or review the final transaction receipt/audit report. | The printed receipt and system audit logs should accurately reflect the actual physical routing of the notes, showing LKR 2000 notes allocated to the All-In-One cassette and other denominations assigned to their respective cassettes. |  |  | CRM Cash Deposit / Cassette Management & Reporting Module | N/A | High | High | Open | Channel Team | 2026-08-14 | Development Team | [5 empty] | Although physical routing and vault accounting are correct, the receipt/report data mismatch causes confusion during daily cash balancing and reconciliation. |  |  | Pending | Pending
CRM V1 | N/A | During cash retraction scenarios where uncollected cash or rejected notes are automatically pulled back into the internal retract bin, the generated SOP / host receipt fails to display the specific cash amounts and piece counts for the items routed into the reject bin. | 1. Initiate a cash transaction (such as a cash deposit or withdrawal) that triggers a cash presentation. 2. Leave the cash or rejected notes uncollected in the shutter until the collection timeout expires. 3. Allow the machine to perform the automated retraction into the internal reject/retract bin. 4. Print or review the final SOP / host transaction receipt. | The SOP / host receipt should accurately display a detailed breakdown of the retracted cash, including both the specific monetary amounts and the exact piece counts of the notes sent to the reject/retract bin. |  |  | CRM Cash Handling / Retraction & Receipt Generation Module | N/A | High | High | Open | Channel Team | 2026-08-14 | Development Team | [5 empty] | Omission of reject bin amounts on the host receipt complicates balancing, auditing, and troubleshooting uncollected cash incidents. |  |  | Pending | Pending
CRM V1 | N/A | When the system's retract count threshold is reached (currently hardcoded or set to a maximum limit of 2 consecutive retract transactions), performing more than 2 retract scenarios causes the machine to block all cassettes and go into an "Out of Service" state. Although the machine eventually returns to an "In Service" state, it remains permanently locked or unresponsive, preventing the execution of any further transactions. | 1. Perform cash deposit or withdrawal transactions that result in uncollected cash retracts. 2. Exceed the configured limit by triggering more than 2 consecutive retract cycles. 3. Observe the machine transition to "Out of Service", recover to "In Service", and then attempt to initiate a new transaction. | The machine should either support an unlimited number of retract cycles (or a configurable high-volume threshold) without locking down cassettes, or automatically recover full transaction capabilities once returning to the "In Service" state without requiring manual administrative intervention. |  |  | CRM Hardware Control / Cassette Security & Error Handling Module | N/A | High | High | Open | Channel Team | 2026-08-15 | Development Team | [5 empty] | This restriction and subsequent permanent lockout severely disrupts machine uptime and requires unnecessary manual resets after multiple normal uncollected cash events. |  |  | Pending | Pending
CRM V1 | N/A | Upon completion of a transaction, the generated SOP receipt and the Host receipt display conflicting information regarding transaction details, resulting in an unreconciled mismatch between the two records. | 1. Execute a standard cash transaction. 2. Complete the transaction workflow. 3. Trigger the printing/generation of both the SOP receipt and the Host receipt. 4. Compare the financial data (amounts, counts) between the two outputs. | The SOP receipt and Host receipt must display identical, validated transaction information, ensuring that all financial records tally correctly for reconciliation purposes. |  |  | CRM / Transaction Reporting & Receipt Module | N/A | High | High | Open | Channel Team | 2026-08-17 | Development Team | [5 empty] | The lack of data consistency between SOP and Host receipts prevents accurate daily balancing and creates significant reconciliation errors. |  |  |  | Pending
CRM V1 | N/A | Following a cash withdrawal retraction, the physical machine entered an "Out of Service" state, yet the Front-End (FE) application incorrectly continued to display the status as "In Service". Additionally, upon restarting the machine to clear the fault and bringing it back "In Service", the vendor's specified threshold of 2 allowed retracts before lockout is inconsistent or prematurely triggered. | 1. Perform a cash withdrawal transaction that triggers a retract. 2. Observe the machine's actual hardware status versus the Front-End (FE) status display. 3. Check if the FE displays "In Service" while the hardware is physically "Out of Service". 4. Restart the machine to restore "In Service" mode and evaluate the retract count behavior against the vendor-specified 2-retract limit. | The Front-End (FE) status must accurately synchronize and reflect the actual hardware state (displaying "Out of Service" when locked), and the retract threshold counter must operate reliably according to the vendor specification without throwing desynchronized states. |  |  | CRM Front-End Status Monitoring & Hardware Communication Module | N/A | High | High | Open | Channel Team | 2026-08-17 | Development Team | [5 empty] | The discrepancy between the FE status and actual hardware status misleads operators, masking machine downtime and making remote monitoring unreliable. |  |  |  | Pending
CRM V1 | N/A | When generating the total receipt list, the deposit counters show an 'All-in-One' cassette total amount that conflicts with and differs from the actual physical cassette-wise denomination breakdown amounts. | 1. Perform deposit transactions containing various denominations routed to the All-in-One cassette and other physical cassettes. 2. Complete the transaction session. 3. Print or review the total receipt list / summary report. 4. Compare the 'All-in-One' deposit counter amount against the actual physical cassette denomination amounts. | The total receipt list's deposit counters for the All-in-One cassette must match precisely with the actual physical cassette-wise denomination amounts without discrepancies. |  |  | CRM Cash Deposit / Counter Reconciliation & Reporting Module | N/A | High | High | Open | Channel Team | 2026-08-17 | Development Team | [5 empty] | Discrepancies between receipt counters and physical cassette totals hinder daily cash balancing and auditing accuracy. |  |  |  | Pending
CRM V1 | N/A | Actual Results: When attempting to change the PIN number on the credit card screen, the screen mapping fails, resulting in a blank or unresponsive 'green screen' error state. | 1. Navigate to the credit card menu / options. 2. Select the option to change the PIN number. 3. Attempt to proceed with the PIN change workflow. 4. Observe the UI response leading to the green screen error. | The PIN change workflow should smoothly navigate through the proper UI screens without failing or freezing into a green screen error. |  |  | CRM Credit Card / PIN Management & UI Navigation Module | N/A | High | High | Open | Channel Team | 2026-08-17 | Development Team | [5 empty] | Screen mapping failure halts credit card PIN modification workflows entirely, causing transaction failure and poor user experience. |  |  |  | Pending