## Defect Tracking Register
IT-TMP-027-Defect Tracking Register Template
|  |  |  | GRG - UAT DEFECT TRACKING REGISTER | [10 empty] | Version: 1.0
Effective Date: 11/08/2026
[11 empty] | For the period from: | 11/08/2026 |  | to | 11/08/2026
PART 1: PROJECT INFORMATION
Program Name | GRG CRM Banking Solution | [7 empty] | Program # |  |  | IT PM
Project Name | People's Bank CRM Testing & Integration | [7 empty] | Project # |  |  | Business PM
Project Sponsor | People's Bank IT Department | [7 empty] | Project Manager |  |  | Project Start Date
PART 2: DEFECTS
Origin (Build) | Defect No. | Defect Description | Steps to Reproduce | Expected Results | Defect Attachment | CR Reference | Application / Module | Defect Category | Severity | Priority | Defect Status | Detected By | Date of Defect Origin | Assigned To | Expected Date of Closure | Fixing Date | Closed By | Date of Closure | SLA = (Date of Closure - Expected date of Closure) | Comments
CRM V1 | TC_CD_CB_N_01_009 | Test case not applicable. For the "Press Cancel on telephone entry screen" scenario, this is invalid as there is no screen for telephone number entry in the current flow. | Press Cancel on telephone entry screen | Transaction cancelled, card ejected, and thank you screen displayed. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Not applicable
CRM V1 | TC_CD_CB_N_01_010 | Invalid remarks entry (rules defined or enforced for remarks field) | Enter remarks violating validation rules | Invalid information or character limit warning message displayed. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | No validation rules defined or enforced for remarks field.
CRM V1 | TC_CB_BP_PIC_PLC_N_01_005 | For Dialog bill payments transaction allowed for 9 digits invalid telephone number | Enter invalid telephone number and confirm | Error information message displayed. |  |  | Card Based PIC PLC-Negetive | Card Based | Medium | Medium | Open | Channel Team |  | Development Team | [5 empty] | Telephone number is not validating.
CRM V1 | TC_CB_CW_P_01_007 | E-receipt unavailable, If there's paper receipt unavailable it's not asking for E-receipt option and transaction proceed successfully without any receipt | Insert Card > Select PIN > Select Withdrawal > Accept "No Receipt / E-Receipt" prompt > Enter amount > Confirm | Cash dispensed successfully, e-receipt/SMS sent to mobile number, no paper printed, card ejected. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | E-receipt option is unavailble.
CRM V1 | TC_CL_BP_P_01_011 |  | Select payment > Receipt unavailable > Agree e-receipt message > Complete valid payment flow | Transaction completed successfully and e-receipt sent |  |  | Cardless Bill Payment-Positive | Cardless | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | No e receipt option available.
CRM V1 | TC_CB_CW_P_01_008 | Verify multiple consecutive cash withdrawals in a single session | Insert Card > Select PIN > Perform 1st Withdrawal > Take Cash > Select Another Transaction > Perform 2nd Withdrawal > Confirm | Both transactions complete successfully, individual CBS debit postings recorded, receipts issued, and card ejected at end. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | There’s no “would you like another service” screen
CRM V1 | TC_CB_CR_P_01_003 | Credit card function is not working, if we try to do any transaction it shows as "Last Transaction Cancelled" | Insert card & enter PIN > Select 'Cash Advance’ > Input custom amount (LKR 15,000) > Confirm. | 1. LKR 15,000 cash dispensed. 2. Balance updated in SIBS. 3. Receipt generated. 4. Card returned. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Last transaction cancelled
CRM V1 | TC_CB_CD_P_01_004 | 10 Digits validated only, phone number is not verified | Enter valid telephone number and confirm | Telephone verified through SV and purpose screen displayed. |  |  | Card_Based_Cash Deposit-Positiv | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | phone number is not verified
CRM V1 | TC_CB_BP_PIC_PLC_P_01_004 | Need to be developed Service charge agree or disagree screen. | Enter valid telephone number and confirm | Process continues with charge confirmation. |  |  | Card Based PIC PLC-Positive | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Need to be developed Service charge agree or disagree screen.
CRM V1 | TC_CD_CB_N_01_008 | When we performing payments through card it doesn't have telephone number entry | Enter telephone number failing API/SV validation | Error prompt displayed on screen. |  |  | CardBased Cash Deposit-Negative | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Not applicable
CRM V1 | TC_CB_SLIC_GENERAL_N_01_001 | When an invalid or non-existent SLIC General Insurance customer reference number is entered it’s not giving any error message | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select SLIC > Select General Insurance > Enter Invalid Customer Reference Number > Enter Amount > Select Account > Confirm Bill Payment | System displays an error message (e.g., "Invalid Customer Reference") and prevents proceeding to confirmation. |  |  | Card_Based_SLIC_GENERAL_Negative | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Customer Ref number is not verified, Ref no - 123456789 amount - 500 acc - 204200260002632
CRM V1 | TC_CB_SLIC_LIFE_N_01_001 | When an invalid or non-existent SLIC Life Insurance customer reference number is entered it’s not giving any error message | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select SLIC > Select Life Insurance > Enter Invalid Customer Reference Number > Enter Amount > Select Account > Confirm Bill Payment | System displays an error message (e.g., "Invalid Customer Reference") and blocks the transaction from completing. | TC_CB_SLIC_LIFE_N_01_001_17864238333255983866130094259887.jpg |  | Card_Based_SLIC_LIFE_Negative | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Customer Ref number is not verified
CRM V1 | TC_CB_CW_N_01_011 | If one cassette is empty, all cassette showing as blocked and can’t perform withdrawal | Insert Card > Enter PIN > Select Withdrawal > Enter valid amount | System should process successfully without errors |  |  | Card Based Cash Withdrawal-Nega | Card Based | Medium | Moderate | Open | Channel Team |  | Development Team | [5 empty] | If one cassette is empty, all cassette showing as blocked and cant perform withdrawal
CRM V1 | TC_CB_CR_P_01_001 | Credit card function is not working, if we try to do any transaction it shows as "Last Transaction Cancelled" | Insert Mastercard > Select Language > Enter valid PIN > Select 'Balance Inquiry’ > Press 'Proceed'. | 1. Screen displays Actual & Available balance. 2. Receipt printed with RRN & STAN/UTANO. 3. Card ejected cleanly. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-09 00:00:00 | Development Team | [5 empty] | Last transaction cancelled
CRM V1 | TC_CB_CR_P_01_002 |  | Insert card & enter PIN > Select 'Cash Advance’ > Select preset amount (LKR 10,000) > Confirm transaction. | 1. Cash dispensed (LKR 10,000). 2. Limit reduced in SIBS. 3. Receipt printed with RRN/UTANO. 4. Card ejected. |  |  | Credit_Card_Positive_Scenario | Card Based | Medium | Moderate | Open | Channel Team | 2026-08-10 00:00:00 | Development Team | [5 empty] | Last transaction cancelled
CRM V1 | TC_CB_CW_P_01_004 | If we request more than daily limit (Eg:>200000) machine gives following 2 screens instead of "daily limit exceed" screen 1. Unable to dispense, sorry for the inconvenience, Thank you for banking with us. 2. Unable to dispense, Enter the multiple of (amount) | Insert Card > Select PIN > Select Withdrawal > Enter max single transaction limit (e.g., Rs. 40,000 / Rs. 100,000) > Confirm | System processes max limit, dispenses notes, updates SIBS/CBS balance, and prints receipt. |  |  | Card Based Cash Withdrawal-Posi | Card Based | Medium | Medium | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | "daily limit exceed" screen is not displayed
CRM V1 | TC_CB_CW_OBC_P_01_001 | Other bank card navigation is completely wrong for the all language | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Saving Account > Enter valid amount(eg - Rs.5000.00) > Take cash | Transaction is approved, cash is dispensed, receipt is printed, and card is returned successfully. |  |  | Other Bank Card function - Positive | Card Based | High | High | Open | Channel Team | 2026-08-11 00:00:00 | Development Team | [5 empty] | Some function are missing in all 3 language
CRM V1 | TC_CB_CW_OBC_P_01_002 | For other banks card pin entry, machine doesn’t allowed transactions for 4 digits pin entry. It’s allowed for only 6 digit pin entry. | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Current Account > Enter valid amount(eg - Rs.5000.00) > Take cash | Transaction is processed successfully, cash is dispensed, and physical/digital receipt is provided. |  |  | Other Bank Card function - Positive | Card Based | High | High | Open | Channel Team | 2026-08-11 | Development Team | [5 empty] | PIN entries not functioning properly
CRM V1 | Card Reader / Initialization Flow | Verify system behavior when a card is inserted and immediately navigates to the language selection screen, but intermittently displays a "Last Transaction Cancelled" message and rejects the card. | Insert Card > Navigate immediately to the language selection screen | The system handles the card read state without false cancellation triggers; if an exception or intermittent timeout occurs, it displays the specific "Last Transaction Cancelled" warning message cleanly, ejects/rejects the card safely, and resets to the welcome screen without locking up the card reader module. |  |  | N/A | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | When we get the journal log it showed as “PIN PAD FAILED” “506 /\ 14:22:32 INSERVICE MODE 14:22:32 798 /\ 14:22:32 INSERVICE MODE 14:22:32 820 SCREEN : 021 14:22:34 285 && PINPAD FAILED, CANCEL TRANSACTION 14:25:53 615 14:25:53 615 2026/08/11 14:25:53 SYSTEM STARTUP 14:25:53 615 ********************************** 14:25:53 617 KERNEL VERSION:3.0.2.906 14:25:53 617 PROJECT VERSION:ECAT(PB_P2800NL)3.0.2.906(XDC)-B8 14:25:53 617 ATM NUMBER:72172128 14:25:53 617 BANK NUMBER:1234 14:25:53 617 BRANCH NUMBER:5678 14:25:53 617 ATM TYPE:P2800NL 14:25:53 646 LOCAL IP:10.230.98.27 14:25:53 646 HOST IP:(ATMP1):172.18.25.114:6000
CRM V1 | Cash Withdrawal Amount Entry UI | Verify system behavior when a user enters an amount (e.g., 123456.00) on the withdrawal amount entry screen and touches the first digit after the decimal point (6), checking if it unexpectedly navigates backward to the transaction type selection screen. | Insert Card > Select Language > Enter valid. PIN > Select Withdrawal > Select Current Account > Enter valid amount 123456.00 > Touch the first digit after the decimal point (6) | The system maintains focus on the input field or correctly handles the touch input without triggering a navigation event; it should not unexpectedly jump backward to the transaction type selection screen. |  |  | N/A | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Bug / Defect: Touch coordinate mapping or event listener on the numeric keypad/decimal input field is misconfigured, causing it to double-fire or misinterpret the touch action as a "Back" or "Cancel" command. Needs UI component re-mapping.
CRM V1 | TC_CB_Sup_N_01_010 | Through the Admin card without receipt if we try to get the list total it gave message as "Transaction successful, Would you like another transaction", through terminal if we try to get E-journal it gave error message as "Print unsuccessfully" | Select Print Audit Report / EJ Journal | System detects paper out status, displays "Printer Paper Empty" error, and logs report to electronic journal. |  |  | Admin _ Supervisor Functions-Ne | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Through the Admin card without receipt if we try to get the list total it gave message as "Transaction successful, Would you like another transaction", through terminal if we try to get E-journal it gave error message as "Print unsuccessfully"
CRM V1 | TC_CB_CR_P_01_001 | Credit card bill payment is not working | Insert Card > Select Language > Enter valid PIN > Select Bill Payment > Select Credit Card bill payment > Enter Invalid Account Number > Enter Amount > Select Account > Confirm Bill Payment | Transaction is processed successfully, and physical receipt is provided and card is ejected |  |  | Card_Based_Credit_Positive | Card Based | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | Credit card bill payment is not working
CRM V2 | Cabinet / Safe Door Interlock Switch | Verify that opening the physical cabinet/safe door of the GRG machine correctly triggers the hardware interlock switch to take the machine out of "In-Service" and transition it into "Supervisor / Maintenance Mode". | Physically open the cabinet/safe door of the GRG machine > Observe the application screen and machine status | The system immediately detects the open door signal, takes the machine "Out of Service" for normal customer transactions, and automatically prompts or transitions into the Supervisor / Maintenance Mode interface. |  |  | N/A | N/A | High | High | Open | Channel Team | 2026-08-12 | Development Team | [5 empty] | The hardware limit switch, door microswitch, or signal line to the mainboard is failing to register the door opening event, or the software service handler is ignoring the interlock input. This poses a security and operational compliance risk.